## Cover
Quartely Progress Report n°2: Q2/2016
Project name: | Capljina Water Supply- Project Implementation
Contract no.: | C24731/CZDT-2012-02-02/a1
Last edit done by: | PIU Capljina | Date: | 11.08.2016.
Sharing policy: For internal project purposes only.
Capljina Water Supply System
Project Implementation Support

## Content (hidden)
Capljina Water Supply System - Project Implementation Support CONTENT
Content |  |  | External general project documents
|  |  | 1 | Loan terms
1 | Budget |  | 2 | Link to MS Project if needed
2 | Financial analysis |  | 3 | Concept review
3 | Action Log |  | 4 | Final review
4 | Risk&Issue Log |  | 5 | Board approval
5 | Project Implementation Plan
6 | Tenders
7 | Conditions precedent
8 | Covenants
9 | Disbursement
10 | Contacts

## Budget (hidden)
1. FEES
ORIGINAL BREAKDOWN OF COSTS |  |  | BILLED |  | REMAINING TO BILL |  |  | MONTHLY SUMMARY
|  | EUR |  | EUR |  | EUR |  | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | TOTAL
ORIGINAL BREAKDOWN OF COSTS |  |  | BILLED |  | REMAINING TO BILL
Miscellaneous |  | Total |  | Total |  | Total
Advance |  | 28000 |  | 28000 |  | 0 | plan | 28000 | [29 empty] | 28000
[7 empty] | actuals | 28000 | [29 empty] | 28000
PIP | Payment against acceptance | 65823 |  | 65823 |  | 0 | plan |  | 65823 | [28 empty] | 65823
[7 empty] | actuals |  | 65823 | [28 empty] | 65823
TD | Payment against acceptance | 46076.1 |  | 46076.1 |  | 0 | plan | [8 empty] | 16455.75 | 16455.75 | 13164.6 | [19 empty] | 46076.1
[7 empty] | actuals | [11 empty] | 46076.1 | [18 empty] | 46076.1
TER | Payment against acceptance | 19956 |  | 19956 |  | 0 | plan | [10 empty] | 9978 | 9978 | [18 empty] | 19956
[7 empty] | actuals | [14 empty] | 19956 | [15 empty] | 19956
Quarterly Progress Report (Q4/13; Q1/14; Q2/14; Q3/14) | Payment against acceptance | 59800 |  | 0 |  | 59800 | plan | [20 empty] | 27800 |  |  |  | 16000 |  |  | 16000 |  |  | 59800
[7 empty] | actuals | [30 empty] | 0
Final Report | Payment against acceptance | 19814.9 |  | 0 |  | 19814.9 | plan | [29 empty] | 19814.9 | 19814.9
[7 empty] | actuals | [30 empty] | 0
MISCELLANEOUS TOTAL |  | 239470 |  | 159855.1 |  | 79614.9 |  | 28000 | 65823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46076.1 | 0 | 0 | 19956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159855.1
ORIGINAL BREAKDOWN OF COSTS |  |  | BILLED |  | REMAINING TO BILL
Contingencies |  | Total |  | Total |  | Total
Utilisation only after prior approval in writing by the Bank |  | 10000 |  | 0 |  | 10000 | plan | [9 empty] | 10000 | [20 empty] | 10000
[7 empty] | actuals | [30 empty] | 0
TOTAL CONTINGENCIES |  | 10000 |  | 0 |  | 10000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL MAXIMUM CONTRACT AMOUNT |  | 249470 |  | 159855.1 |  | 89614.9 |  | 28000 | 65823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46076.1 | 0 | 0 | 19956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159855.1

## EAV (hidden)
Legend: The graph shows Planned Value (blueline) which is based on the planned effort in financial terms for each task in the project plan and split into months for the overall project duration. This planned value is compared to the Actual Cost (redline) which is based on monthly budget spent on fees and updated spending of the budget for future period. Finally the graph shows Earned Value (greenline) which is a variable based on the budgeted value of work completed on cumulative basis. Automatically updated on monthly basis. Last revision: 28.3.2014
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS) - to be planned at the beginning of project, not to be changed later
WBS | Activity Name | TBC | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01
1 | Project Inception (20MDs) | 28000 | 14000 | 14000
2 | Project Implementation Plan (40MDs) | 65823 | 16456 | 16456 | 16456 | 16455
3 | Tender 1 (40 MDs) | 16455.75 | [5 empty] | 4114 | 2057 | 2057 | 4114 | 2057 | 823 | 823 | 410.75
4 | Tender 2 (22 MDs) | 13164.6 | [7 empty] | 2992 |  | 2992 | 2992 | 1795 | 1197 | 598 | 598.6
5 | Tender 6 (42 MDs) | 16455.75 | [5 empty] | 3918 | 1959 | 1959 | 3918 | 1959 | 1175.4 | 1175.4 | 391.95
6 | Tender Evaluation Report 1 (8 MDs) | 9978 | [11 empty] | 4989 | 4989
7 | Tender Evaluation Report 6 (8 MDs) | 9978 | [18 empty] | 4989 | 4989
8 | Quarterly Reporting 1,2, 3, 4 (20 MDs) | 59800 | [20 empty] | 14950 |  | 14950 |  | 14950 |  |  | 14950
9 | Final Report (10 MDs) | 19814.9 | [28 empty] | 9907.45 | 9907.45
10 | Contingency (10 MDs) | 10000 | [21 empty] | 10000
Insert new rows above this one
Total Budgeted Cost (in EUR) |  | 249470 | 30456 | 30456 | 16456 | 16455 | 0 | 8032 | 4016 | 7008 | 8032 | 7008 | 4990.4 | 8782.4 | 6988.7 | 598 | 598.6 | 0 | 0 | 0 | 4989 | 4989 | 14950 | 10000 | 14950 | 0 | 14950 | 0 | 0 | 14950 | 9907.45 | 9907.45
Cumulative Planned Value (PV) |  |  | 30456 | 60912 | 77368 | 93823 | 93823 | 101855 | 105871 | 112879 | 120911 | 127919 | 132909.4 | 141691.8 | 148680.5 | 149278.5 | 149877.1 | 149877.1 | 149877.1 | 149877.1 | 154866.1 | 159855.1 | 174805.1 | 184805.1 | 199755.1 | 199755.1 | 214705.1 | 214705.1 | 214705.1 | 229655.1 | 239562.55 | 249470
Actual Cost and Earned Value - not to be changed; updated automatically | [9 empty] | 0
| Cumulative Actual Cost (AC) |  | 30456 | 60912 | 77368 | 93823 | 93823 | 101855 | 105871 | 112879 | 120911 | 127919 | 132909.4 | 141691.8 | 148680.5 | 149278.5 | 149877.1 | 149877.1 | 149877.1 | 149877.1 | 154866.1 | 159855.1 | 174805.1 | 184805.1 | 199755.1 | 199755.1 | 214705.1 | 214705.1 | 214705.1 | 229655.1 | 239562.55 | 249470
| Cumulative Earned Value (EV) |  | 30456 | 60912 | 77368 | 93823 | 93823 | 101855 | 105871 | 112879 | 120911 | 127919 | 132909.4 | 141691.8 | 148680.5 | 149278.5 | 149877.1 | 149877.1 | 149877.1 | 149877.1 | 154866.1 | 159855.1 | 174805.1 | 184805.1 | 199755.1 | 199755.1 | 214705.1 | 214705.1 | 214705.1 | 229655.1 | 239562.55 | 249470
Actual Cost (AC) of Work Performed - to be updated on monthly basis
WBS | Task Name |  | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01
1 | Project Inception |  | 2012-08-01: 14000; 2012-09-01: 14000
2 | Project Implementation Plan |  | 2012-08-01: 16456; 2012-09-01: 16456; 2012-10-01: 16456; 2012-11-01: 16455
3 | Tender 1 |  | 2013-01-01: 4114; 2013-02-01: 2057; 2013-03-01: 2057; 2013-04-01: 4114; 2013-05-01: 2057; 2013-06-01: 823; 2013-07-01: 823; 2013-08-01: 410.75
4 | Tender 2 |  | 2013-03-01: 2992; 2013-05-01: 2992; 2013-06-01: 2992; 2013-07-01: 1795; 2013-08-01: 1197; 2013-09-01: 598; 2013-10-01: 598.6
5 | Tender 6 |  | 2013-01-01: 3918; 2013-02-01: 1959; 2013-03-01: 1959; 2013-04-01: 3918; 2013-05-01: 1959; 2013-06-01: 1175.4; 2013-07-01: 1175.4; 2013-08-01: 391.95
6 | Tender Evaluation Report 1 |  | 2013-07-01: 4989; 2013-08-01: 4989
7 | Tender Evaluation Report 6 |  | 2014-02-01: 4989; 2014-03-01: 4989
8 | Quarterly Reporting 1,2,3,4 |  | 2014-04-01: 14950; 2014-06-01: 14950; 2014-08-01: 14950; 2014-11-01: 14950
9 | Final Report |  | 2014-12-01: 9907.45; 2015-01-01: 9907.45
10 | Contingency |  | 2014-05-01: 10000
Insert new rows above this one | bar: 2012-08-01 to 2013-07-01
|  | Total Actual Cost | 30456 | 30456 | 16456 | 16455 | 0 | 8032 | 4016 | 7008 | 8032 | 7008 | 4990.4 | 8782.4 | 6988.7 | 598 | 598.6 | 0 | 0 | 0 | 4989 | 4989 | 14950 | 10000 | 14950 | 0 | 14950 | 0 | 0 | 14950 | 9907.45 | 9907.45
|  | Cumulative Actual Cost (AC) | 30456 | 60912 | 77368 | 93823 | 93823 | 101855 | 105871 | 112879 | 120911 | 127919 | 132909.4 | 141691.8 | 148680.5 | 149278.5 | 149877.1 | 149877.1 | 149877.1 | 149877.1 | 154866.1 | 159855.1 | 174805.1 | 184805.1 | 199755.1 | 199755.1 | 214705.1 | 214705.1 | 214705.1 | 229655.1 | 239562.55 | 249470
Cumulative Earned Value (EV) - to be updated on monthly basis
WBS | Task Name | TBC | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01
1 | Project Inception | 28000 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Project Implementation Plan | 65823 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Tender 1 | 16455.75 | 0% | 0% | 0% | 0% | 0% | 25% | 37.5% | 50% | 75% | 87.5% | 92.5% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Tender 2 | 13164.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73% | 22.73% | 45.46% | 68.18% | 81.82% | 90.91% | 95.45% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Tender 6 | 16455.75 | 0% | 0% | 0% | 0% | 0% | 23.81% | 35.71% | 47.62% | 71.43% | 83.33% | 90.48% | 97.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Tender Evaluation Report 1 | 9978 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Tender Evaluation Report 6 | 9978 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Quarterly Reporting 1,2,3,4 | 59800 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100%
9 | Final Report | 19814.9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100%
10 | Contingency | 10000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Insert new rows above this one | bar: 2012-08-01 to 2013-07-01
Cumulative EV |  |  | 30456 | 60912 | 77368 | 93823 | 93823 | 101855 | 105871 | 112879 | 120911 | 127919 | 132909.4 | 141691.8 | 148680.5 | 149278.5 | 149877.1 | 149877.1 | 149877.1 | 149877.1 | 154866.1 | 159855.1 | 174805.1 | 184805.1 | 199755.1 | 199755.1 | 214705.1 | 214705.1 | 214705.1 | 229655.1 | 239562.55 | 249470

## Financial analysis
Capljina Water Supply System - Project Implementation Support FINANCIAL ANALYSIS
Financial analysis - Company
Ratio Analysis (EUR) | [9 empty] | Income Statement
| 2012 | 2013 | 1H 2014 | 2014 | 1H 2015 | 2015 | 1H 2016 | 2016 |  |  | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016 | 2016
Covenanted Ratios / levels | [8 empty] | 1 | Revenue | 1456701.7583 | 1580400 | 688371 | 1582964 | 708934 | 1534607 | 725068
3.03 (b) DSCR / @ 1.3 < | 3.2671 | 34.341 | 7759.8182 | -597.6885 | -25382.2 | -180186.65 | -4143.4196 |  | 2 | Cost of Sales | 0 | 0 | 0 |  | 0 | 0 | 0
3.03 (c) Revenue / Collected / @ >0.95 | 0.97124 | 0.92598 | 1.9702 | 0.41021 | 2.1272 | 0.98271 | 1.0764 |  | 3 | SGA | -1368093.3414 | -1451372 | -606959 | -1276316 | -816963 | 1705145 | 717423
3.03 (a) Current Ratio / @ 1.1 < | 6.303 | 1.0483 | 2.6146 | 0.43464 | 0.39095 | 0.56307 | 0.56448 |  | 4 | EBITDA | 88608.4169 | 129028 | 81412 | 306648 | -108029 | 3239752 | 1442491 | 0 | 0 | 0
3.03 (d) Receivables /@ 0.1 > | 0.075405 | 0.069405 | 0.13881 | 0.11504 | 0.086551 | 0.080056 | 0.068681
Other Ratios | [8 empty] | 5 | Depreciation | -81422.7208 | -119487 | -77666 | -306116 | -76286 | -304615 | -152414
T.L. / T. N. W. / @ xy | 0.072001 | 0.44205 | 0.11244 | 0.6179 | 2.2659 | 2.7056 | 3.0891 |  | 6 | EBIT | 7185.6961 | 9541 | 3746 | 532 | -184315 | 2935137 | 1290077 | 0 | 0 | 0
Return on Sales | 0.3199% | 0.302% | 0.5769% | 0.07075% | -26.02% | 202.4% | 177.5% |  | 7 | Interest Expense | -4289.2276 | -4330 | -11 | -61 | -20 | -20 | -1020
Return on Assets | 0.1285% | 0.09742% | 0.1101% | 0.03091% | -2.651% | 37.43% | 14.02% |  | 8 | Other Costs/Income | 2280.8731 | 22 | 236 | 460 | -164 | 171586 | -2121
Net Margin | 0.3199% | 0.302% | 0.5769% | 0.07075% | -26.02% | 202.4% | 177.5% |  | 9 | Profit before tax | 5177.3416 | 5233 | 3971 | 931 | -184499 | 3106703 | 1286936 | 0 | 0 | 0
EBITDA Margin | 6.083% | 8.164% | 11.83% | 19.37% | -15.24% | 211.1% | 198.9% |  | 10 | Tax incurred | -517.9387 | -460 | 0 | -189 | 0 | -102 | 0
Receivables (Days) | 336.1262 | 329.3966 | 414.4542 | 104.8572 | 321.8132 | 160.7277 | 392.901 |  | 11 | Profit after tax | 4659.4029 | 4773 | 3971 | 1120 | -184499 | 3106805 | 1286936 | 0 | 0 | 0
Payables (Days) | 170.4776 | 189.2066 | 468.9395 | 182.8175 | 449.8902 | 266.7089 | 932.4535 |  | 12 | Dividends | 0 | 0 | 0 |  |  | 0 | 0
Depreciation/Capex | 242% | 113% | 46.89% | 113.4% | -12.43% | -83.71% | -26.71% |  | 13 | Other Items | 0 | 0 | 0 |  |  | 0 | 0
Sales/Fixed Assets | 76.96% | 47.53% | 25.95% | 52.39% | 11.46% | 20.49% | 8.791% |  | 14 | Profit for the year | 4659.4029 | 4773 | 3971 | 1120 | -184499 | 3106805 | 1286936 | 0 | 0 | 0
[9 empty] | 15 | Change in Net Worth | 0 | 0 | 0 |  |  | 0
Miscellaneous | [9 empty] | Balance Sheet
| 2012 | 2013 | 1H 2014 | 1H 2015 | 2015 |  | 1H 2016 |  |  |  | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016
SGA | [8 empty] | 16 | Cash | 44746.2203 | 17091 | 27244 | 15681 | 21762 | 14169 | 28735
Employees | 1014872 | 1007704 | 729933 | 437186 | 902523 |  | 425630 |  | 17 | Receivables | 1341467.3054 | 1426242 | 781639 | 454754 | 625053 | 675764 | 780493
Other costs | 228446 | 206241 | 128920 | 303490 | 498001 |  | 223379 |  | 18 | Inventories | 125781.8931 | 126863 | 139868 | 129532 | 125554 | 122835 | 125025
Collected receivables during year | [8 empty] | 19 | Other Advances | 3663.9176 | 4303 | 4078 | 1429 | 0 | 0 | 0
Collected receivables per TB | 1414804 | 1463415 | 1356259 | 649345 | 1508075 |  | 780493 |  | 20 | Total Current Assets | 1515659.3364 | 1574499 | 952829 | 601396 | 772369 | 812768 | 934253 | 0 | 0 | 0
Aggregate amount of receivables not paid for more than 180 days | 101153 | 98989 | 108500 | 52315 | 54099 |  | 53605 |  | 21 | Fixed Assets | 1892756.0166 | 3325047 | 2652563 | 3021582 | 6187019 | 7488425 | 8247743
[9 empty] | 22 | Other Assets | 217637.5247 | 0 | 0 |  | 0 | 0
[9 empty] | 23 | Total Assets | 3626052.8778 | 4899546 | 3605392 | 3622978 | 6959388 | 8301193 | 9181996 | 0 | 0 | 0
[9 empty] | 24 | Trade payables | 106698.4349 | 106910 | 165632 | 152009 | 613824 | 363894 | 570659
[9 empty] | 25 | Taxes payable | 14651.5801 | 8472 | 12623 | 10472 | 218546 | 107799 | 112655
[9 empty] | 26 | Accrued expenses | 0 | 1308648 | 99394 | 1143254 | 0 | 0 | 0
[9 empty] | 27 | Other ST Liabilities | 119117.2034 | 77887 | 86771 | 77931 | 1143244 | 971766 | 971765
[9 empty] | 28 | Total Current Liab | 240467.2185 | 1501917 | 364420 | 1383666 | 1975614 | 1443459 | 1655079 | 0 | 0 | 0
[9 empty] | 29 | Long Term Debt (EBRD) | 3076.9545 | 0 | 0 |  | 2852864 | 4617582 | 5281431
[9 empty] | 30 | Other LT Liabilities | 0 | 0 | 0 |  |  | 0 | 0
[9 empty] | 31 | Total Liabilities | 243544.1731 | 1501917 | 364420 | 1383666 | 4828478 | 6061041 | 6936510 | 0 | 0 | 0
[9 empty] | 32 | Equity | 3382508.7047 | 3397629 | 3240972 | 2239312 | 2130910 | 2240152 | 2245486
[9 empty] | 33 | Total Liab & Equity | 3626052.8778 | 4899546 | 3605392 | 3622978 | 6959388 | 8301193 | 9181996 | 0 | 0 | 0
[10 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash-Flow Statement
[11 empty] | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016
[9 empty] | 34 | Operating Profit (EBIT) | 7185.6961 | 9541 | 3746 | 532 | -184315 | 2935137 | 1290077
[9 empty] | 35 | Depreciation & Amortisation (+) | 81422.7208 | 119487 | 77666 | 306116 | 76286 | 304615 | 152414
[9 empty] | 36 | Gross Operating CF (EBITDA) | 88608.4169 | 129028 | 81412 | 306648 | -108029 | 3239752 | 1442491 | 0 | 0 | 0
[9 empty] | 37 | Changes in Working Capital (+/-) | -135590.0053 | -1551778 | -1138 |  | 1849 | 189 | 2213138
[9 empty] | 38 | Other non-cash adjustments | 11228.481 | 1437370 | 21652 |  | 3043080 | 4464491 | 1953120
[9 empty] | 39 | Tax Paid | -4689.0578 | -4141 | -17519 |  | 0 | 0 | 0
[9 empty] | 40 | Other Costs/Income | -2008.3545 | -4177 | 138 |  | 0 | 0 | 0
[9 empty] | 41 | Net Operating CF | -42450.5197 | 6302 | 84545 | 306648 | 2936900 | 7704432 | 5608749 | 0 | 0 | 0
[9 empty] | 42 | Interest received | 217.8103 | 22 | 236 |  | 0 | 0 | 0
[9 empty] | 43 | Debt repaid | -20548.3094 | -40194 | 0 |  | 0 | 0 | 0
[9 empty] | 44 | Dividends Paid | 0 | 0 | 0 |  | 0 | 0 | 0
[9 empty] | 45 | Pre Investment CF | -62781.0188 | -33870 | 84781 | 306648 | 2936900 | 7704432 | 5608749 | 0 | 0 | 0
[9 empty] | 46 | Capital Expenditure | -33648.1187 | -105787 | -165632 | -270000 | 613824 | 363894 | 570659
[9 empty] | 47 | Pre Financing CF | -96429.1375 | -139657 | -80851 | 36648 | 3550724 | 8068326 | 6179408 | 0 | 0 | 0
[9 empty] | 48 | EBRD new Debt | 0 | 0 | 0 |  | 0 | 0 | 0
[9 empty] | 49 | Other new Debt | 22543.8816 | 38117 | 0 |  | 0 | 0 | 0
[9 empty] | 50 | Change in Net Worth | 0 | 0 | 0 |  | 0 | 0 | 0
[9 empty] | 51 | Post Financing CF | -73885.2559 | -101540 | -80851 | 36648 | 3550724 | 8068326 | 6179408 | 0 | 0 | 0
[10 empty] | Cash End | 44746.2203 | 17091.4762 | 37780.4762 | 155279.4762 | 3669355.4762 | 8186957.4762 | 6298039.4762 | 118631.4762 | 118631.4762 | 118631.4762
[10 empty] | As per BS | 44746.2203 | 17091 | 27244 | 15681 | 21762 | 14169 | 28735 | 0 | 0 | 0
[10 empty] | diff | 2.161e-09 | 0.47615 | 10536.4762 | 139598.4762 | -3647593.4762 | -8172788.4762 | -6269304.4762 | -118631.4762 | -118631.4762 | -118631.4762
Note on E7: user: The ratio cannot be calculated as loan repayment has not begun yet.
Note on Q70: The Loan repayment will begin on Aug 15, 2014, therefore there is the difference in the amount of 10,536.

## Cover
Quartely Progress Report n°4: Q4/2016
Project name: | Capljina Water Supply- Project Implementation
Contract no.: | C24731/CZDT-2012-02-02/a1
Last edit done by: | PIU Capljina | Date: | 13.03.2017.
Sharing policy: For internal project purposes only.
Capljina Water Supply System
Project Implementation Support

## Financial analysis
Capljina Water Supply System - Project Implementation Support FINANCIAL ANALYSIS
Financial analysis - Company
Ratio Analysis (EUR) | [9 empty] | Income Statement
| 2012 | 2013 | 1H 2014 | 2014 | 1H 2015 | 2015 | 1H 2016 | 2016 |  |  | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016 | 2016
Covenanted Ratios / levels | [8 empty] | 1 | Revenue | 1456701.7583 | 1580400 | 688371 | 1582964 | 708934 | 1534607 | 725068 | 1530717
3.03 (b) DSCR / @ 1.3 < | 3.2671 | 34.341 | 7759.8182 | -597.6885 | -25382.2 | -180186.65 | -4143.4196 | -4117.7804 | 2 | Cost of Sales | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
3.03 (c) Revenue / Collected / @ >0.95 | 0.97124 | 0.92598 | 1.9702 | 0.41021 | 2.1272 | 0.98271 | 1.0764 | 0.48203 | 3 | SGA | -1368093.3414 | -1451372 | -606959 | -1276316 | -816963 | 1705145 | 717423 | 1666770
3.03 (a) Current Ratio / @ 1.1 < | 6.303 | 1.0483 | 2.6146 | 0.43464 | 0.39095 | 0.56307 | 0.56448 | 0.54919 | 4 | EBITDA | 88608.4169 | 129028 | 81412 | 306648 | -108029 | 3239752 | 1442491 | 3197487 | 0 | 0
3.03 (d) Receivables /@ 0.1 > | 0.075405 | 0.069405 | 0.13881 | 0.11504 | 0.086551 | 0.080056 | 0.068681 | 0.29889
Other Ratios | [8 empty] | 5 | Depreciation | -81422.7208 | -119487 | -77666 | -306116 | -76286 | -304615 | -152414 | -476163
T.L. / T. N. W. / @ xy | 0.072001 | 0.44205 | 0.11244 | 0.6179 | 2.2659 | 2.7056 | 3.0891 | 3.6537 | 6 | EBIT | 7185.6961 | 9541 | 3746 | 532 | -184315 | 2935137 | 1290077 | 2721324 | 0 | 0
Return on Sales | 0.3199% | 0.302% | 0.5769% | 0.07075% | -26.02% | 202.4% | 177.5% | 177.9% | 7 | Interest Expense | -4289.2276 | -4330 | -11 | -61 | -20 | -20 | -1020 | -1020
Return on Assets | 0.1285% | 0.09742% | 0.1101% | 0.03091% | -2.651% | 37.43% | 14.02% | 26.06% | 8 | Other Costs/Income | 2280.8731 | 22 | 236 | 460 | -164 | 171586 | -2121 | 2762
Net Margin | 0.3199% | 0.302% | 0.5769% | 0.07075% | -26.02% | 202.4% | 177.5% | 177.9% | 9 | Profit before tax | 5177.3416 | 5233 | 3971 | 931 | -184499 | 3106703 | 1286936 | 2723066 | 0 | 0
EBITDA Margin | 6.083% | 8.164% | 11.83% | 19.37% | -15.24% | 211.1% | 198.9% | 208.9% | 10 | Tax incurred | -517.9387 | -460 | 0 | -189 | 0 | -102 | 0 | 0
Receivables (Days) | 336.1262 | 329.3966 | 414.4542 | 104.8572 | 321.8132 | 160.7277 | 392.901 | 209.27 | 11 | Profit after tax | 4659.4029 | 4773 | 3971 | 1120 | -184499 | 3106805 | 1286936 | 2723066 | 0 | 0
Payables (Days) | 170.4776 | 189.2066 | 468.9395 | 182.8175 | 449.8902 | 266.7089 | 932.4535 | 1079.4401 | 12 | Dividends | 0 | 0 | 0 |  |  | 0 | 0 | 0
Depreciation/Capex | 242% | 113% | 46.89% | 113.4% | -12.43% | -83.71% | -26.71% | -47.49% | 13 | Other Items | 0 | 0 | 0 |  |  | 0 | 0 | 0
Sales/Fixed Assets | 76.96% | 47.53% | 25.95% | 52.39% | 11.46% | 20.49% | 8.791% | 16.28% | 14 | Profit for the year | 4659.4029 | 4773 | 3971 | 1120 | -184499 | 3106805 | 1286936 | 2723066 | 0 | 0
[9 empty] | 15 | Change in Net Worth | 0 | 0 | 0 |  |  | 0 |  | 0
Miscellaneous | [9 empty] | Balance Sheet
| 2012 | 2013 | 1H 2014 | 1H 2015 | 2015 |  | 1H 2016 | 2016 |  |  | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016 | 2016
SGA | [8 empty] | 16 | Cash | 44746.2203 | 17091 | 27244 | 15681 | 21762 | 14169 | 28735 | 58066
Employees | 1014872 | 1007704 | 729933 | 437186 | 902523 |  | 425630 | 851572 | 17 | Receivables | 1341467.3054 | 1426242 | 781639 | 454754 | 625053 | 675764 | 780493 | 877625
Other costs | 228446 | 206241 | 128920 | 303490 | 498001 |  | 223379 | 339034 | 18 | Inventories | 125781.8931 | 126863 | 139868 | 129532 | 125554 | 122835 | 125025 | 110834
Collected receivables during year | [8 empty] | 19 | Other Advances | 3663.9176 | 4303 | 4078 | 1429 | 0 | 0 | 0 | 0
Collected receivables per TB | 1414804 | 1463415 | 1356259 | 649345 | 1508075 |  | 780493 | 737857 | 20 | Total Current Assets | 1515659.3364 | 1574499 | 952829 | 601396 | 772369 | 812768 | 934253 | 1046525 | 0 | 0
Aggregate amount of receivables not paid for more than 180 days | 101153 | 98989 | 108500 | 52315 | 54099 |  | 53605 | 262314 | 21 | Fixed Assets | 1892756.0166 | 3325047 | 2652563 | 3021582 | 6187019 | 7488425 | 8247743 | 9402146
[9 empty] | 22 | Other Assets | 217637.5247 | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | 23 | Total Assets | 3626052.8778 | 4899546 | 3605392 | 3622978 | 6959388 | 8301193 | 9181996 | 10448671 | 0 | 0
[9 empty] | 24 | Trade payables | 106698.4349 | 106910 | 165632 | 152009 | 613824 | 363894 | 570659 | 1002649
[9 empty] | 25 | Taxes payable | 14651.5801 | 8472 | 12623 | 10472 | 218546 | 107799 | 112655 | 73863
[9 empty] | 26 | Accrued expenses | 0 | 1308648 | 99394 | 1143254 | 0 | 0 | 0 | 0
[9 empty] | 27 | Other ST Liabilities | 119117.2034 | 77887 | 86771 | 77931 | 1143244 | 971766 | 971765 | 829065
[9 empty] | 28 | Total Current Liab | 240467.2185 | 1501917 | 364420 | 1383666 | 1975614 | 1443459 | 1655079 | 1905577 | 0 | 0
[9 empty] | 29 | Long Term Debt (EBRD) | 3076.9545 | 0 | 0 |  | 2852864 | 4617582 | 5281431 | 6297876
[9 empty] | 30 | Other LT Liabilities | 0 | 0 | 0 |  |  | 0 | 0 | 0
[9 empty] | 31 | Total Liabilities | 243544.1731 | 1501917 | 364420 | 1383666 | 4828478 | 6061041 | 6936510 | 8203453 | 0 | 0
[9 empty] | 32 | Equity | 3382508.7047 | 3397629 | 3240972 | 2239312 | 2130910 | 2240152 | 2245486 | 2245218
[9 empty] | 33 | Total Liab & Equity | 3626052.8778 | 4899546 | 3605392 | 3622978 | 6959388 | 8301193 | 9181996 | 10448671 | 0 | 0
[10 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash-Flow Statement
[11 empty] | 2012 EUR | 2013 EUR | 1H 2014 EUR | 2014 EUR | 1H 2015 EUR | 2015 EUR | 1H 2016 | 2016
[9 empty] | 34 | Operating Profit (EBIT) | 7185.6961 | 9541 | 3746 | 532 | -184315 | 2935137 | 1290077 | 2721324
[9 empty] | 35 | Depreciation & Amortisation (+) | 81422.7208 | 119487 | 77666 | 306116 | 76286 | 304615 | 152414 | 476163
[9 empty] | 36 | Gross Operating CF (EBITDA) | 88608.4169 | 129028 | 81412 | 306648 | -108029 | 3239752 | 1442491 | 3197487 | 0 | 0
[9 empty] | 37 | Changes in Working Capital (+/-) | -135590.0053 | -1551778 | -1138 |  | 1849 | 189 | 2213138 | 0
[9 empty] | 38 | Other non-cash adjustments | 11228.481 | 1437370 | 21652 |  | 3043080 | 4464491 | 1953120 | 2095251
[9 empty] | 39 | Tax Paid | -4689.0578 | -4141 | -17519 |  | 0 | 0 | 0 | 0
[9 empty] | 40 | Other Costs/Income | -2008.3545 | -4177 | 138 |  | 0 | 0 | 0 | 0
[9 empty] | 41 | Net Operating CF | -42450.5197 | 6302 | 84545 | 306648 | 2936900 | 7704432 | 5608749 | 5292738 | 0 | 0
[9 empty] | 42 | Interest received | 217.8103 | 22 | 236 |  | 0 | 0 | 0 | 0
[9 empty] | 43 | Debt repaid | -20548.3094 | -40194 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | 44 | Dividends Paid | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | 45 | Pre Investment CF | -62781.0188 | -33870 | 84781 | 306648 | 2936900 | 7704432 | 5608749 | 5292738 | 0 | 0
[9 empty] | 46 | Capital Expenditure | -33648.1187 | -105787 | -165632 | -270000 | 613824 | 363894 | 570659 | 1002649
[9 empty] | 47 | Pre Financing CF | -96429.1375 | -139657 | -80851 | 36648 | 3550724 | 8068326 | 6179408 | 6295387 | 0 | 0
[9 empty] | 48 | EBRD new Debt | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | 49 | Other new Debt | 22543.8816 | 38117 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | 50 | Change in Net Worth | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | 51 | Post Financing CF | -73885.2559 | -101540 | -80851 | 36648 | 3550724 | 8068326 | 6179408 | 6295387 | 0 | 0
[10 empty] | Cash End | 44746.2203 | 17091.4762 | 37780.4762 | 155279.4762 | 3669355.4762 | 8186957.4762 | 6298039.4762 | 6414018.4762 | 118631.4762 | 118631.4762
[10 empty] | As per BS | 44746.2203 | 17091 | 27244 | 15681 | 21762 | 14169 | 28735 | 58066 | 0 | 0
[10 empty] | diff | 2.161e-09 | 0.47615 | 10536.4762 | 139598.4762 | -3647593.4762 | -8172788.4762 | -6269304.4762 | -6355952.4762 | -118631.4762 | -118631.4762
Note on E7: user: The ratio cannot be calculated as loan repayment has not begun yet.
Note on Q70: The Loan repayment will begin on Aug 15, 2014, therefore there is the difference in the amount of 10,536.

## Risk&Issue Log
Capljina Water Supply System - Project Implementation Support RISK REGISTER
Area/ Tender | Possible risk event | Risk cause | Impact | Severity | Mitigation | Risk Owner | Due date | Status
Design | Preparation of the Technical specifications is taking longer than expected | Insufficient capacity of the Clients personnel Lack of technical documentation | Delayed tendering process and construction start | MEDIUM | Increased effort and exact deadlines planning, operative reporting: Document preparation readiness will be compared to the dates in the Document Inventory every second weeks | Municipality/PIU | 2014-03-31 | PENDING
Procurement | Scope of the tenders 3 and 5 is not confirmed entirely – design or detailed specification is not ready | Uncertainty in the scope to be taken into account when preparing draft TOR for tender 6 | Delayed tendering process and construction start | MEDIUM | PIU to make decisions on specification of the respective tenders (based on FOPIP) | Municipality/PIU | 31.03.2014. | CLOSED
Procurement | Missing construction permits for Trebizat area | Changes in designs of investments | Delayed tendering process and construction start | MEDIUM | To accelerate works to obtain construction permits for Trebizat areas | Municipality/PIU | 30.09.2014. | CLOSED
Conditions Precedent | Non effectiveness of Loan Agreement since remaining condition precedent is not fulfilled yet | Agreements validation is taking longer than planned | Stopping of the project | HIGH | Increased effort to ensure grant agreement execution and delivery is ratified | EBRD | See Section CONDTITIONS PRECEDENT STATUS OVERVIEW | CLOSED
Loan covenants | Disbursements not done as per PIP since financial loan covenants not provided to EBRD | Data not ready from Komunalno | Delayed tendering process and construction start | HIGH | Accelerate the accounting analysis and provide Financial loan covenants reports to EBRD / Suggest Komunalno to employ person responsible for financial reporting to EBRD | Komunalno | Financial covenants submitted to EBRD on 23 April 2014 | CLOSED
Loan covenants | Difficulty in reporting loan covenants to EBRD on time decreases chances for timely disbursement | Need for enhanced information exchange between Municipality and Komunalno | Delayed tendering process and construction start | HIGH | Ensure fluent information exchange between the two entities by regular monthly information exchange meetings | Municipality/Komunalno | Ms. Alić Cvitanović and Ms. Vidić from JKP became members of PIU Decision is available here: https://www.dropbox.com/s/zgsawqcc1nutbe7/CAP_Decision%20on%20the%20Composition%20of%20PIU.pdf | CLOSED

## Project Implementation Plan 2 (hidden)
Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN
Approved
Expected
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  | 13 | 14 | 10 | 11 | 12 |  |  |  | 13 | 14 | Comments
No | Description | Estimated Contract Value | Financing by EBRD | Financing by others |  | Contract Type | Procurement Method | Subject to Selective review | Prequal Invitation mmm/yy | Prequal results mmm/yy | Tender invitation mmm/yy*1 | No objection - TD*2 | TOS | No objection - TER | Contract Award mmm/yy | Contract Completion mmm/yy | Prequal Invitation mmm/yy | Prequal results mmm/yy | Tender invitation mmm/yy | No objection - TD | TOS | No objection - TER | Contract Award mmm/yy | Contract Completion mmm/yy
|  |  |  | Financier | Amount
Works
1* | Construction of Backbone pipelines 1.1 - LOT 1 (Dubrave area) 1.2 - LOT 2 (Trebizat, Prcavci, Zvirovici) | 2900 | 1000 | EC | 1900 | Works | Open |  |  |  | 2013-01-01 | 2013-02-01 | 2013-02-15 | 2013-05-13 | 2013-05-11 | 2014-03-07 | 0 | 0 | -57 | 41306 | 41320 | 41407 | -204 | -208
|  | 2200 | 1000 |  | 1200 | [5 empty] | 2013-02-27 |  |  |  | 2013-12-01 | 2014-10-01
2* | Construction of Pumping stations and water tanks 2.1 - LOT 1 (Dubrave area) 2.2 - LOT 2 (Trebizat, Prcavci, Zvirovici and water tank Centar area) | 3000 | 1700 | EC | 1300 | Works | Open |  |  |  | 2013-02-01 | 2013-02-28 | 2013-04-15 | 2013-06-13 | 2013-06-21 | 2014-03-28 | 0 | 0 | -150 | 41333 | 41379 | 41438 | -194 | -218
|  | 2530 | 1058 |  | 1472 | [5 empty] | 2013-07-01 |  |  |  | 2014-01-01 | 2014-11-01
3* | Construction of Distribution network for: 3.1 - LOT 1 (Trebizat, Prcavci, Zvirovici) 3.2 - LOT 2 Dubrave area | 2500 | 1800 |  | 700 | Works | Open |  |  |  | 2013-05-01 |  |  |  | 2013-09-28 | 2014-10-13 | 0 | 0 | -365 | 0 | 0 | 0 | -276 | -200
|  | 3200 | 1462 |  | 1738 | [5 empty] | 2014-05-01 |  |  |  | 2014-07-01 | 2015-05-01
4 | Procurement and installment of water meter | 400 | 200 |  | 400 | Goods | Local competitive |  |  |  | 2013-05-01 |  |  |  | 2013-06-20 | 2013-10-18 | 0 | 0 | -365 | 0 | 0 | 0 | 41445 | 41565
|  | 200 |  |  | 0 | [5 empty] | 2014-05-01
5* | Improvement of functioning of the existing water supply network by 5.1-5.4) | 200 | 960 |  | 200 | Works | Open |  |  |  | 2013-05-01 |  |  |  | 2013-06-20 | 2013-10-18 | 0 | 0 | -365 | 0 | 0 | 0 | -376 | -499
|  | 960 |  |  | 0 | [5 empty] | 2014-05-01 |  |  |  | 2014-07-01 | 2015-03-01
6 | Technical Assistance Contract Supervision for works, under No.1 – No.5 | 500 | 500 | - |  | Consultancy | Competitive |  |  |  | 2013-01-01 | 2013-02-18 | 2013-04-19 | 2013-05-16 | 2013-05-31 |  | 0 | 0 | -90 | 41323 | 41383 | 41410 | -184 | -42095
|  | 270 | 270 | [7 empty] | 2013-04-01 |  |  |  | 2013-12-01 | 2015-04-01
7 | Front end fee | 50 | 50
8 | Grant management fee | 90 |  |  | 90
| Total: | 9500 | 5000 |  | 4500
1* Amount without VAT (No-objection issued)
2*Amount without VAT (evaluation procedure is ongoing)
3* Estimated amount by Designer
5*
5.1* Including Water well in water supply system
5.2 Reconstruction of electric part of well field Bjelave
5.3 Construction of chlorine station
5.4 Decrease of water loses in the existing network by reconstruction of existing network in the central area as well as decreasing of pressure
Formulas:
Contract Award mmm/yy = [Tender invitation mmm/yy*1]+130
Contract Completion mmm/yy = [Contract Award mmm/yy]+300

## Project Implementation Plan
Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN*
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 10 | 11 | 12 |  |  |  | 13 | 14 | Comments
No | Description | Estimated Contract Value | Contracted Value/Revised value | Financing by EBRD | Financing by others |  | Contract Type | Procurement Method | Subject to Selective review | Prequal Invitation mmm/yy | Prequal results mmm/yy | Tender invitation mmm/yy*1 | Contract Award mmm/yy | Contract Completion mmm/yy | Prequal Invitation mmm/yy | Prequal results mmm/yy | Tender invitation mmm/yy | No objection - TD | TOS | No objection - TER | Contract Award mmm/yy | Contract Completion mmm/yy
[5 empty] | Financier | Amount
1(1) | Construction of Backbone pipelines | 2900 | 2740 | 1120 | EC (Grant) | 1620 | Works | Open |  |  |  | Feb-13 | Dec-13 | Dec-15
| 1.1 - LOT 1 (Dubrave area) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 1710(1.1.); Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 553; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 1157
| 1.2 - LOT 2 (Trebizat, Prcavci, Zvirovici) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 1030(1.2); Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 567; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 463
2(2) | Construction of Pumping stations and water tanks | 3000 | 2689 | 1311 | EC (Grant) | 1378 | Works | Open |  |  |  | Jul-13 | Jan-14 | Fe-16
| 2.1 - LOT 1 (Dubrave area) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 1585(2.1); Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 724; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 861
| 2.2 - LOT 2 (Trebizat, Prcavci, Zvirovici and water tank Centar area) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 1104(2.2); Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 587; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 517
3(3) | Construction of Distribution network for | 2500 | 2434 | 1022 | EC (Grant) | 1412 | Works | Open |  |  |  | May-15 | Oct-15 | Feb-17
| 3.1 –LOT 1 Dubrave area (cca 20km Gradnina and Bat) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 1003; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 297; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 706
| 3.2. -LOT 2 Dubrave area (cca 20km; Križ and Pijano Brdo)) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 900; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 194; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 706
| 3.3 – LOT 3 (Trebizat, Prcavci, Zvirovici) (20 km) |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 531; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 531
4 | Procurement of water meter; water and sewerage material | 400 | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 270; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 270; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 7: Goods; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 8: Open; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 12: Marc-15 | July-15 | Oct-15
| 4.1. -LOT 1:Water meter |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 183; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 183
| 4.1. -LOT 2:Water and sewerage material |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 87; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 87
5 | Pumping station Bjelave | 200 | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 594; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 594; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 7: Works; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 8: Open; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 12: Apr-16 | Jun-16 | Mar-17
Tehnical Assistance
6 | Contract Supervision for works, under No.1 – No.5 |  | 402 | 402 | - | - | Consul. | Competitive |  |  |  | Apr-13 | Dec-13 | Apr-17
7 | Leak repair and monitoring of the existing system and improving the quality and realiability of the water supply. |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 231; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 231; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 7: Works; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 8: Open; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 12: Dec-16 | Mar-17 | May-17
8 | Front End Fee |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 50; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 50
9 | Grant management fee |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 90; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 90
| Total: |  | Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 3: 9500; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 4: 5000; Capljina Water Supply System - Project Implementation Support PROJECT IMPLEMENTATION PLAN* 6: 4500
|  |  |  | 5000 |  | 4500
(1) Contract(s) and approved Amendment(s): amount without VAT.
(2) Contract(s) and approved Amendment(s): amount without VAT.
(3) The contract(s) were signed.
(4) Amount without VAT
(5) Pumping station Bjelave (involvement of new water well in the existing water supply system; rehabilitation of the central pumping station Bjelave - electrical part, etc);
(7) Leak repair and monitoring cover reduction of losses in the existing system (detection of leak, repair of detected leaks, measurement of the flow rate and pressure in zones, etc).

## Tenders
2017-06-23 |  | Capljina Water Supply System - Project Implementation Support PROGRESS ON TENDERS
2017-07-13
PROCUREMENT ACTIVITY |  | T1 |  |  |  | T2 |  |  |  | T3 |  |  |  | T4 |  |  |  | T5 |  |  |  | T6-tech. Assis |  | T7
Technical specification | Scheduled | Expected | Comment | Status | Scheduled | Expected | Comment | Status | Scheduled | Expected | Comment | Status | Scheduled | Expected | Comment | Status | Scheduled | Expected | Comment | Status | Scheduled | Expected | Status | Expected | Comment | Status
Terms of Reference – draft (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-01-21 | 2013-01-21 | DONE | N/A |  | N/A
Terms of Reference – final (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-02-04 | 2013-03-01 | DONE | N/A |  | N/A
Technical documents – draft | 2012-10-20 | 2012-12-07 | Documents prepared and sent for translation and then for review | DONE | 2013-01-30 | 2013-07-03 | Documents prepared and sent for translation and then for review | DONE |  | 2014-09-30 |  | DONE |  | Sep-14 |  | DONE |  | Feb-15 |  | DONE | N/A | N/A | N/A
Technical documents – reviewed by WPE | 2013-01-11 | 2013-01-11 | Finalized to be included in the Tender Document | DONE |  | 2013-07-05 |  | DONE |  | 2015-02-28 |  | DONE |  | Sep-14 |  | DONE |  | Feb-15 |  | DONE | N/A | N/A | N/A
Technical documents – final | 2013-01-11 | 2013-01-11 | Finalized to be included in the Tender Document | DONE | 2013-02-15 | 2013-07-05 | Finalized and included in the Tender Document | DONE |  | 2015-03-05 |  | DONE |  | Sep-14 |  | DONE |  | Feb-15 |  | DONE | N/A | N/A | N/A
Tender documentation
Tender Document – draft | 2013-01-16 | 2013-01-16 | Prepared and sent for comments to PIU | DONE | 2013-02-01 | 2013-07-05 | Draft for approval by the Mayor | DONE |  | 2015-04-10 |  | DONE |  | Sep-14 |  | DONE |  | Mar-16 |  | DONE | N/A | N/A | N/A | Jul-16 |  | OPEN
Tender Document – final | 2013-02-01 | 2013-02-04 | Finalized and sent to the Bank | DONE | 2013-02-20 | 2013-07-17 | Final ready to be sent to the Bank | DONE |  | 2015-05-18 |  | DONE |  | Sep-14 |  | DONE |  | Apr-16 |  | DONE | N/A | N/A | N/A | Jul-16 |  | OPEN
Tender Document – no-objection | 2013-02-15 | 2013-02-22 | Bank’s review and no-objection granted | DONE | 2013-02-28 | 2013-08-19 | Bank´s review and no-objection granted | DONE |  | 2015-06-01 |  | DONE |  | 2015-03-23 |  | DONE |  | 12.4.2016. |  | DONE | N/A | N/A | N/A | Aug-16 |  | OPEN
Tendering
Invitation for Expressions of Interest (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-02-18 | 2013-03-28 | DONE
Request for Proposal – draft (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-01-14 | 2013-04-12 | DONE
Request for Proposal – final (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-01-17 | 2013-04-19 | DONE
Request for Proposal – no-objection (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-01-24 | 2013-04-29 | DONE
Deadline for Expresssions of Interest (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-02-28 | 2013-04-30 | DONE
Short list – final (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-03-05 | 2013-05-06 | DONE
Short list – no-objection (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-03-12 | 2013-05-13 | DONE
RFP distributed to shortlisted firms (T6 only) |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-03-12 | 2013-07-01 | DONE
Invitation to Tender | 2013-02-15 | 2013-02-27 | Published | DONE | 2013-02-28 | 2013-08-23 | To be published | DONE |  | 2015-06-01 |  | DONE |  | 2015-03-24 |  | DONE |  | 2016-04-15 |  | DONE | N/A | N/A | N/A | 2016-08-15 |  | DONE
Tender Opening Session | 2013-03-15 | 2013-04-15 |  | DONE | 2013-04-15 | 2013-10-07 | To be followed by evaluation | DONE |  | 2015-07-16 |  | DONE |  | 2015-05-08 |  | DONE |  | 2016-06-02 |  | DONE | 2013-04-19 | 2013-08-16 |  | 2016-10-01 |  | DONE
Tender Evaluation Report – draft | 2013-04-05 | 2013-06-25 | Draft for approval by the Mayor | DONE | 2013-05-06 | 2014-02-14 | Draft for approval by the Mayor | DONE |  | 2015-08-15 |  | DONE |  | 2015-06-07 |  | DONE |  | 2016-06-15 |  | DONE | 2013-04-26 | 2013-08-30 | DONE | 2016-10-31 |  | OPEN
Tender Evaluation Report – final | 2013-04-23 | 2013-07-12 | Final ready to be sent to the Bank | DONE | 2013-05-20 | 2014-02-26 | Final ready to be sent to the Bank | DONE |  | 2015-09-30 |  | DONE |  | 2015-06-12 |  | DONE |  | 2016-06-22 |  | DONE | 2013-05-03 | 2013-09-06 | DONE | 2016-11-05 |  | OPEN
Tender Evaluation Report – no-objection | 2013-05-13 | 2013-07-31 | Bank’s review and no-objection granted | DONE | 2013-06-13 | 2014-03-06 | Bank´s review and no-objection granted | DONE |  | 2015-10-09 |  | DONE |  | 2015-06-17 |  | DONE |  | 2016-06-24 |  | DONE | 2013-05-16 | 2013-09-13 | DONE | 2016-11-10 |  | OPEN
Contracting
Contract award | 2013-05-16 | 2013-08-07 | Subject to Conditions Precedent / T6 signed | DONE | 2013-06-17 | 2014-03-10 | Subject to Conditions Precedent / T6 signed | DONE |  | 2015-10-14 |  | DONE |  | 2015-06-30 |  | DONE |  | 2016-06-23 |  |  | 2013-05-24 | 2013-09-20 | DONE | 2016-11-15 |  | OPEN
Contract agreement signed | 2013-05-31 | 2013-09-04 | Subject to Conditions Precedent / T6 signed | DONE | 2013-06-30 | 2014-04-07 | Subject to Conditions Precedent / T6 signed | DONE |  | 2015-11-03 |  | DONE |  | 2015-07-16 | DONE | DONE | 5.03.2015. | 2016-07-01 | OPEN | DONE | 2013-10-04 | 2013-10-04 | DONE | 2016-11-15 |  | OPEN
Formulas:
T3 = [T3, row above]+5
T2 = [T2, row above]+45
T4 = [T4, row above]+45
T5 = [T5, row above]+7

## Contract (hidden)
Legend: The sheet shows the list of relevant project documentation regarding the scope of the project and related links to them. The sheet to be updated on monthly basis. Last revision: 28.3.2014
Pre-project documents regarding scope | Project documentation regarding scope | Project deliverables
Proposal (incl. out-of-scope definition) | FOPIP | Inception report
TOR | Project Implementation Plan | T1 - Tender Document
Contract | Working strategy 22.4.2013 | T6 -RFP
Subco contracts | Contract Amendment 1 | T6 - Evaluation of EOIs
Prime contract | Contract Amendment 2 | T2 - Tender Document
Grant agreement
Loan agreement
Project agreement
Project support agreement
ESAP
Time Schedule (.mpp)

## Disbursement
Capljina Water Supply System - Project Implementation Support DISBURSEMENT
No | Description | Estimated Contract Value | Contracted Value/Revised value | Financing by EBRD | Financing by others |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017
[5 empty] | Financier | Amount |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Works
1 | Construction of Backbone pipelines 1.1 - LOT 1 (Dubrave area) 1.2 - LOT 2 (Trebizat, Prcavci, Zvirovici) | 2900000 | 2740000 | 1120 | EC | 1620 | Plan | 0 | 550000 | 550000 | 550000 | 550000 | 750000 | 320000 | 360000 | 300000 | 0 | 485000
[7 empty] | Actual | 0 | 440000 | 0 | 307690.53 | 142943.33 | 749932 | 137131.58 | 179643 | 297803 | 0 | 484500
2 | Construction of Pumping stations and water tanks 2.1 - LOT 1 (Dubrave area) 2.2 - LOT 2 (Trebizat, Prcavci, Zvirovici and water tank Centar area) | 3000000 | 2689000 | 1311 | EC | 1378 | Plan | 0 | 506000 | 506000 | 506000 | 506000 | 610000 | 163000 | 440000 | 200000 | 315000 | 300000 | 944000 | 732000
[7 empty] | Actual | 0 | 0 | 510729.8 | 0 | 186339.43 | 610664 | 116747.23 | 46295 | 170885 | 170383.49 | 0 | 144762
3 | Construction of Distribution network for 3.1 -LOT 1 Dubrave area(cca 20km Gradina and Bat) 3.2-LOT 2 Dubrave area (cca 20 km Kriz and Pijano brdo) 3.3-LOT 3 Trebizat,Prcavci,Zvirovici (cca 20 km) | 2500000 | 2434000 | 1022 | EC | 1412 | Plan | 0 | 0 | 0 | 640000 | 640000 | 0 | 0 | 486000 | 100000 | 280000 | 900000 | 550000 | 100000 | 698000
[7 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106250 | 98386 | 141200 | 701216 | 589328.25
4 | Procurement of water meter;water and sewerage material | 400000 | 270000 | 270 |  |  | Plan | 0 | 0 | 40000 | 40000 | 40000 | 125000 | 175000 | 270000
[7 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270587
5 | Pumping station Bjelave | 200000 | 594000 | 594 | - |  | Plan | 0 | 192000 | 192000 | 192000 | 192000 | 0 | 225000 | 0 | 0 | 0 | 200000 | 100000 | 100000 | 286000
[7 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118739 | 89304
6 | Technical Assistance Contract Supervision for works, under No.1 – No.5 |  | 402000 | 402 | - | - | Plan | 0 | 38571 | 38571 | 38571 | 38571 | 37000 | 32000 | 34000 | 44000 | 43000 | 60000 | 66000 | 25000 | 20000
[7 empty] | Actual | 0 | 54000 | 18904.46 | 17816.46 | 14586.46 | 37217 | 30382 | 53146 | 44228 | 0 | 20446 | 66464
7 | Leak repair and monitoring of the existing system and improving the quality and reliability of the water supply. |  | 231000 | 231 | - | - | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 231000
[7 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total: |  | 9360000 | 4950 | EC | 4410 | Plan | 0 | 1286571 | 1326571 | 1966571 | 1966571 | 1522000 | 915000 | 1590000 | 644000 | 638000 | 2050000 | 1660000 | 957000 | 1235000
[7 empty] | Actual | 0 | 494000 | 529634.26 | 325506.99 | 343869.22 | 1397813 | 284260.81 | 655920 | 611302 | 311583 | 1324901 | 889858.25
Disbursement plan, plan vs actuals
384000

## Contacts (hidden)
Name | Company | Project Role | E-mail | Phone
Dr. Smiljan Vidic | Capljina | Steering Committee, Project management | Nacelnik@capljina.ba | +387 36 805 060,
+387 63 320 766
Josip Polic | EBRD | Steering Committee | policj@ebrd.com | +387 33 667 945/6/7,
+387 61 139 370
Miroslav Kučera | Aspiro | Steering Commitee | miroslav.kucera@aspiro.cz | +421 914 326 810, +90 537 0390527
Daniel Zverko | Aspiro | Steering Committee | daniel.zverko@aspiro.cz | +421 914 326 801
Project management
Dalibor Milinković | Municipality of Capljina | Project management | dalibor.milinkovic@capljina.ba | +387 63 376 673
Mirjana Menalo | Municipality of Capljina | Project management | mirjana.menalo@capljina.ba | +387 63 936 280
Goran Jelavić | Municipality of Capljina | Procurement Specialist | gjelavic@jadran.ba | +387 63 993 503
Adisa Tojaga Kajan | Municipality of Capljina | Procurement Specialist | atojaga@jadran.ba | +387 63 288 751
Ante Maslać | Municipality of Capljina |  | ante.maslac@capljina.ba | +387 63 893 895
Mario Colic | JKP Komunalno | Director | komunalno.capljina@tel.net.ba | +387 63 465 933
Martina Vidić | JKP Komunalno | Officer for development of technical documentation and GIS | vidicmartina7@gmail.com | +387 63 424 808
Marina Alic Cvitanovic | JKP Komunalno | Officer for general, legal and personnel affairs | aliccvitanovicmarina@gmail.com | +387 63 936 048
Martina Kovacova | Aspiro | Project Manager | martina.kovacova@aspiro.cz | +421 914 326 809
Petr Dřevikovský | WPE | Technical Expert - Mechanical/Electrical Engineer | drevikovsky.petr@wpe.cz | +420603501602
Petr Hrnčíř | WPE | Technical Expert – Civil Engineer | p.hrncir@ekos-zitenice.cz | +420 776 057 313
Tomáš Fuka | WPE | Technical Expert - Enviro& Social | Fuka.tomas@wpe.cz | +420 604 655 787
Janja Krndelj | Aspiro/Local |  | j.krndelj@gmail.com | +387 63 343 343, +385 98 980 2390
Robert Leko | Aspiro/Local |  | robert.leko@tel.net.ba | +387 63 326 270
Tomislav Marić | Aspiro/Local |  | zavod.za.vodoprivredu@tel.net.ba | +387 63 313 164, +387 36 317 931
Elio Bošković | Aspiro/Local | Local Expert | elio.boskovic@gmail.com | +387 63 322 428
Željko Dugandžić | Aspiro/Local | Local Expert | brocanac@tel.net.ba | +387 63 376 651
Abida Pehlić | Aspiro | Intrerpreting and coordination | abida_pehlic@yahoo.co.uk | +387 61 240 934
Branko Vucijak | Eptisa | Eptisa Deputy Team Leader | branko.vucijak@heis.com.ba